## Active Issues
ID | Issue Title | Owner | Date Raised | Status | Description | Updates
58 | Concern in relation to the volume of 'Special Order' strengths listed on dm+d | NHSBSA | 2022-10-17 | Open | Concerns that if lots of different strengths of specials for the same medicine are all available for selection on prescribing systems that this is likely to contribute to dosing and patient safety issues. Some expert reputable guidelines also recommend a rational approach here too. | 21/11/2022 - Following receipt of the issue it was discussed at a Content Committee meeting. The Content Committee does not believe it is the role of dm+d to act as a formulary for approved unlicensed medicines but its role is to be a dictionary of specials that are available and required for use by patients. The Committee agreed that it may be pragmatic for dm+d to consider discontinuing Specials where data indicates that they are no longer used. This issue is to remain open with ongoing discussion. 10/01/2023 - The issue raiser was provided with the Content Committee update. 09/02/2023 - The issue raiser welcomes ongoing investigation of the issue and consideration to possibly discontinue some concepts that do not appear to have been used for a defined period of time. The issue raiser would support the listing of selected ‘Special Order' strengths only with input from relevant stakeholders/clinical agencies and the issue raiser would be open for collaborating in this process too. May 2023 - The topic of Specials is being investigated and supported by experts who are leading on the national review of Specials. This is not the dm+d Content Committee. The 'issue' can remain open for the time being. 09/11/2023 - Further dm+d Content Committee discussion took place and this issue was carried over to the next meeting of the committee. 26/02/2024 - The Content Committee requested both primary care and secondary care data on the use of Specials from the last 10 years to see what the numbers would look like. This date is to be made available to the committee for the next Content Committee meeting and an understanding of what the numbers might look like if Specials were to be discontinued on dm+d that hadn’t been used in the last 5 and 10 year time periods.

## Closed Issues
ID | Issue Title | Owner | Date Raised | Status | Date Closed | Description | Updates
47 | Radiopharmaceuticals expression of strength | NHS Digital | 2016-11-15 | Closed | 2017-07-12 | Request to add a radiopharmaceutical to dm+d has highlighted an issue with expression of its strength | 21/11/16 - investigation of how to express the strength of the product has started. 20/01/17 - a proposal to amend the dm+d editorial policy for the expression of strength will be considered by the Content Committee 28/03/17 - the Content Committee has agreed the changes to the editorial policy in principle but requires some further actions to ensure there is no risk to patient safety as a result of not expressing the strength of radiopharmaceuticals in dm+d. 12/07/2017 -the Content Committee agreed that, after confirmation from Dr Sebastian Alexander (Strategic Lead for Patient Safety Solution Assurance/Clinical Safety), that for Radiopharmaceutical isotopes, VMP and AMP concepts on dm+d could be created that identify active moiety, radioisotope and pharmaceutical strength without reference to strength. The clinical risks were considered to be low as each product is prescribed by a clinician and dose would then be specified.
50 | Citalopram 40mg/ml oral drops sugar free dosing instructions | NHS RxS | 2017-01-10 | Closed | 2017-03-28 | For citalopram oral drops, the VMP and AMP descriptions all describe the strength in terms of mg/ml i.e. 40mg/ml. Sometimes the dose is prescribed in terms of mls and sometimes in terms of drops. One drop = 2mg citalopram and one ml = 20 drops. The EMIS GP practice system usage instructions provide dual representation e.g. '4 drops (8mg) to be taken each day.' In contrast the SystmOne usage instructions default to 'use daily' and there have been some incidents where patients have received the wrong dose using the SystmOne clinical system. In order to support the SystmOne clinical system, the issue raiser would like dm+d to add a dose default in 'drops' preferably with a prompt to the prescriber as to the dose to be prescribed similar to what appears in the EMIS system. | 12/01/17 - advised the issue raiser that the AMP names on dm+d follow Part 1 of the SmPCs in line with the dm+d Editorial Policy. Differences between EMIS and SystmOne provide evidence that this is a dm+d implementation issue. dm+d colleagues will consider whether any improvements can be made to guidance that is provided for implementers, however, the expression of 'dose' is primarily addressed by system suppliers. Therefore the enquirer was advised to raise this directly with TPP and the GPSoC team who are involved with GP system suppliers. 25/01/17 - the issue raiser confirmed that they would contact TPP and ask them to make any necessary changes.
48 | Differences in expression of strength between similar VMPs e.g. eye drops | NHS RxS | 2016-11-17 | Closed | 2017-03-28 | Similar products on dm+d may have the strength expressed in different ways. For example latanoprost/timolol eye drops are expressed as mcg/ml, whereas dorzolamide/timolol eye drops are expressed as %. There is an impact on those that read the dispensing labels that use dm+d for their terminology. This issue may have been a contributing factor in the wrong strength being prescribed for a patient. | 22/11/2016 - authoring of these products is guided by the SmPC as the source document. Appendix XX has recently been added to the editorial policy to provide examples of where there are differences in product names on dm+d, including differences in strength, and a brief reason for these differences is included in the new appendix. The issue has been followed up with the MHRA who provided the following explanation 'Concentration of the active substance (strength) for ophthalmic products have previously been expressed as % (w/v or w/w). However, current practice, based on European guideline, is to express the strength as quantity per unit volume or weight (most commonly per unit volume), for example mg/ml or micrograms/ml. Therefore, strength for some old products could still be expressed as % whereas the strength would be in mg/ml or micrograms/ml for most newer products.' Where all the AMPs for a VMP have changed to expressing the strength as quantity per unit volume or weight, the VMP term can be changed to reflect this. Further investigation is required to identify products where the VMP term may need changing. 20/01/17 - an explanation of why these differences in expression of strength arise will be added to the editorial policy. 28/03/17 - the editorial policy has been updated and the new version will be published in May 2017.
49 | Authoring of VMPs for sevelamer | NHS RxS | 2016-11-21 | Closed | 2016-11-30 | There is a single VMP for sevelamer 800mg tablets. Users of dm+d have raised issues that they would find it useful to be able to differentiate the specific salts. This can only be done currently by specifying the AMP to supply. If a patient was unable to tolerate sevelamer carbonate and they are now stable on sevelamer hydrochloride, prescribers would need to select sevelamer hydrochloride and not just sevelamer as the patient could end up with an inappropriate product being dispensed and administered to them. | 22/11/2016 - Previous investigation of this issue, including discussion with the MHRA, has shown that there is no difference in the active parts of the molecules for the hydrochloride and carbonate salts and therefore these have been authored as a single VMP. There are differences in the licensed indications for the AMPs and the products may not be fully interchangeable. Depending on the consultation about introducing a new prescribing status for the VMP, this product could have the new status applied of 'Caution - AMP level prescribing may be advised'. 20/01/17 - The Content Committee agreed that the VMP is authored in line with the editorial policy and that it could in future be indicated with the flag that prescribing at AMP level may be advised.
35 | VMP for lymphoedema garments | NHS RxS | 2014-04-23 | Closed | 2016-11-30 | AMPs that are lymphoedema garments all link to a single VMP ‘Lymphoedema garments’. Over the last few years more companies have marketed lympoedema garments and existing ranges of garments have been extended. This has resulted in 1,000s of AMPs linking to one VMP. The increase in AMPs causes difficulties for the authoring team because it is exceeding the capability of the authoring tool. It also makes it more difficult for dm+d users to browse the data. New lymphoedema garments continue to be added to the Drug Tariff Part IX (over 4,000 AMPs in April alone) and there is an increasing concern that a single VMP is unsustainable. The authoring team is proposing replacing the VMP 'Lymphoedema garments' with more VMPs that better represent the range of products available. | 24/04/14 - investigation of new VMPs that could be created has been initiated by NHS RxS. 14/05/14 - the Content Committee has requested that options for the creation of new VMPs should be explored. 18/08/14 - the Content Committee has agreed that more specific VMPs for lymphoedema garments should be created and the existing AMPs will move to the relevant new VMP. The next step will be an in-depth analysis of the existing AMPs. Input from users of dm+d will be sought to help define the editorial policy for authoring the new VMPs. 23/12/14 - Analysis of the 20,000 AMPs has started and data have been obtained to show which products are being prescribed in primary care. The NHSBSA will be exploring how GP practice and pharmacy IT systems use the dm+d data in picking lists of lymphoedema garments and will be seeking informal feedback from users of dm+d. 12/03/15 - a preliminary list of new VMPs has been compiled. The NHSBSA has investigated how a GP practice and a pharmacy IT system use the dm+d data to generate picking lists of lymphoedema garments. The NHSBSA plans to engage further with system suppliers to ensure the new VMPs are appropriately authored. 13/07/15 - the Content Committee accepted a proposal to create the new VMPs and endorsed the option to group lymphoedema garments into four compression ranges. The NHSBSA authoring team is continuing the work to scope the new VMPs. Feedback has been obtained from system suppliers that supports the case for re-authoring. Work is now starting to identify how to move the AMPs to the new VMPs and the timescales. There will be further communication with dm+d users before any AMPs are moved. 08/10/15 - the NHSBSA is identifying the most appropriate technical solution to move the AMPs to the new VMPs and will then estimate how long it will take to move all the AMPs. 10/02/16 - the NHSBSA is progressing with the development of a technical solution to move the AMPs to the new VMPs. There will be further communication with dm+d users before any AMPs are moved. 14/06/16 - The VMP 'Lymphoedema Garments' can be split into 94 new VMPs and this number may be further increased. The new VMPs have been created in a test environment and the AMPs are being moved across. When testing is complete, the changes will be made to the dm+d data set. A TRUD communication will be sent to recipients of the data to give 3 months advance notice of the changes appearing in the data. 25/07/16 - advance notice of the change has been issued through the TRUD communication with an implementation date of 31 October 2016. 31/10/16 - the changes to lymphoedema garments in the dm+d data are live in the extract files.
45 | Expression of strength in terms of % | NHS RxS | 2016-02-08 | Closed | 2016-08-16 | The British Association of Dermatologists’ List of Preferred Specials includes (and elsewhere prescribers and pharmacists describe) the strength of solutions of trichloroacetic acid (TCA) in water in terms of %weight in volume e.g. 90%w/v. The dm+d doesn’t use the w/v suffix but uses only %. In the case of TCA, which has a relative density of 1.2, there is a 20% difference in TCA content between a solution containing 90%w/w and 90%w/v. This difference is highly clinically significant. | 15/03/16 - the expression of pharmaceutical strength does not usually need to clarify whether a strength expressed as a percentage is based on w/w or w/v and therefore the dm+d does not include reference to w/w or w/v. The most appropriate way to clarify the expression of strength of products such as Trichloroacetic acid 90% solution will be explored. 23/06/16 - the Content Committee agreed that the VMP names will be changed to express the strength of TCA as both a % and as weight in volume e.g. mg/ml. 16/08/16 - the VMP terms have been changed to express the strength as both % and mg/ml.
43 | Reference to BP in names of VMPs that include coal | NHS RxS | 2016-02-08 | Closed | 2016-08-16 | The British Association of Dermatologists’ List of Preferred Specials lists products containing coal in terms of the % of one of the official coal tar preparations of which there are three: Coal Tar BP, Coal Tar Solution BP and Coal Tar Solution Strong, BP. The dm+d VMP name does not use the BP suffix. The issue raisers are concerned that without this there is a risk of clinically significant prescribing and dispensing errors. | 15/03/16 - the Content Committee is already reviewing when (and if) the VMP name should make reference to the British Pharmacopoeia. A proposal to include reference to the BP when it may affect the prescribing/dispensing of the product has been submitted to the committee, who have requested further information about how the proposed editorial policy could be made clear to dm+d users and could be applied objectively. The names of the VMPs that include coal tar will be reviewed after the committee determines the editorial policy for including BP in the VMP name. 23/06/16 - the Content Committee considered that the addition of BP to the VMP names of these products would not remove the risk of a dispenser incorrectly identifying the coal ingredient and therefore did not support including the BP suffix in the name. 16/08/16 - the issue raisers have been updated and the NHSBSA will include information about the risk of providing an incorrect product in the next edition of its bulletins for dispensing contractors and users of the Prescription Services information systems to help raise awareness.
46 | VMP Prescribing Status of Salbutamol 100micrograms/dose inhaler CFC free | NHS RxS | 2016-06-03 | Closed | 2016-08-12 | Glasgow and Clyde Health Board encourages generic prescribing of Salbutamol 100micrograms/dose inhaler CFC free as part of a quality prescribing initiative. The issue raiser has asked why the dm+d data indicates the AMPs of the VMP description Salbutamol 100micrograms/dose inhaler CFC free to be not interchangeable and therefore dm+d does not recommend prescribing at the VMP level. Prescribers using one of the GP practice systems are now warned to prescribe at the AMP level which conflicts with the health board policy. | 14/06/16 - the dm+d Content Committee (CC) requested a change to the value assigned for the VMP prescribing status of inhalation products following meetings with the MHRA that have clarified the way in which products are licensed. The MHRA confirmed that the products are not interchangeable in all groups of patients. They are not considered wholly interchangeable with the innovator product for all the indications and patient populations; there may be differences in e.g. restricted populations and in the administration device which requires different techniques of administration and training. The Content Committee considered that the dm+d data should indicate that prescribing by generic name may not be appropriate for some patients because there is a potential risk to patient safety if the products are not flagged. The Content Committee has decided that users of dm+d should be consulted about potential changes to the flags for assigning the VMP prescribing status and this will include changes that will help resolve this issue. 23/06/16 - the consultation should begin in September 2016. 12/08/16 - an explanation of why the VMP prescribing status has been changed has been provided to the issue raiser.
42 | VMPs for some modified release products | NHS RxS | 2015-11-09 | Closed | 2016-08-03 | The issue raiser has requested that dm+d consider altering the authoring of VMPs for a small number of modified release products with clinically significant differences in release profile. They would like to have separate VMPs to distinguish the products rather than using a single VMP for products of the same strength and form, which are then flagged as not recommended to prescribe using the VMP. | 07/12/15 - similar requests have been made previously (see Issue 10). However there are no European or UK standards to distinguish products with different release profiles and it is not simple to identify when a product would be sufficiently distinct to create a new VMP. The products are authored in line with the editorial policy and therefore the Content Committee will be asked to review options for resolving the issue. 10/02/16 - the Content Committee has reviewed the request but did not consider it appropriate to create separate VMPs to accommodate prescribing by generic name since there is no standard that can be applied to distinguish between VMPs on the basis of their release profile. The Content Committee was concerned that these are products where the MHRA recommends brand name prescribing therefore when the care of the patient is transferred between organisations, information to identify the particular brand the patient has received must be available. The Committee agreed that the value for the VMP prescribing status flag assigned to the products should be reviewed to ensure that the flag supports brand name prescribing. 03/06/16 - the values for the VMP prescribing status for specific products have been reviewed, a potential change to the value assigned to buprenorphine patches is being investigated further. 03/08/16 - the flag for ‘VMP not recommended to prescribe – patient training required’ has been applied to the VMPs for buprenorphine patches.
36 | Difference in expression of strength between VMP name and AMP name | NHS RxS | 2014-09-08 | Closed | 2016-08-03 | Products are sometimes authored in dm+d such that the expression of strength of the active substance(s) in the VMP name is different to the AMP. A recent example is the VMP 'Glycopyrronium bromide 55microgram inhalation powder capsules with device' that has the AMP 'Seebri Breezhaler 44microgram inhalation powder capsules with device (Novartis Pharmaceuticals UK Ltd)'. The way the licence holder has chosen to express the product strength in Part 2 of the Summary of Product Characteristics for Seebri Breezhaler is based on glycopyrronium whereas the strength of the generic VMP is based on glycopyrronium bromide. The VMP has been named in line with the dm+d editorial policy using the rINN. However both Novartis and the dm+d authors have received several enquiries as to why there is a difference, and users of the dm+d data may be unsure whether they have selected the correct VMP to prescribe and the corresponding AMP to dispense. Novartis has also received enquiries from patients concerned about the difference in expression of strength (the dispensing label has a different strength to the packaging). There are other examples where the qualitative and quantitative composition in the SPC is different to how the VMP is named in dm+d and the differences arise for various reasons (not just because of expressing the strength based on the base or salt). | 23/12/14 - a discussion between the MHRA and the dm+d authors to explore the reasons for differences in expression of strength and naming will be arranged. 12/03/15 - The Content Committee will explore options to determine whether it is possible to indicate products where there may be a difference in expression of strength between the VMP and its AMPs. 13/07/15 - the preferred option is to continue current practice in describing the VMPs and AMPs. Information is published with the SNOMED CT release notes document that identifies this issue and provides examples of differences. The Content Committee requested that a list of products be prepared where there is a difference in strength between the VMP and the AMP descriptions. The list will be published with the dm+d documentation and the dm+d authors will identify a suitable location for the list. 08/10/15 - the Content Committee has agreed that due to the length of the list of products, it will be more appropriate to publish a list of instances where differences in expression of strength occur and provide examples of products. 10/02/16 - the Content Committee has approved the list of examples to be published as Appendix XX to the editorial policy. 03/06/16 - the revised editorial policy has been published.
44 | Pomade has no specific dose form | NHS RxS | 2016-02-08 | Closed | 2016-06-23 | The British Association of Dermatologists’ List of Preferred Specials includes the description “Pomade”, a term which is still commonly used by dermatology prescribers for ointments to be applied to the scalp but does not currently appear in dm+d. dm+d policy uses only the term “scalp application” as the dose form for pomades. Whilst this is technically correct for solutions designed for application to the scalp it is potentially misleading to users of electronic prescribing and other software if also applied to ointments intended for scalp application. | 15/03/16 - the dm+d editorial policy is to populate the VMP dose form using the European Directorate for the Quality of Medicines & HealthCare (EDQM) List of Standard Terms. Pomade is not one of the EDQM standard terms. The dose forms for the Specials identified as 'Pomade' in the BAD list will be investigated further to determine if there is an appropriate dose form that can be applied. 03/06/16 - the dm+d authoring teams have discussed with the issue raisers that ointments for application to the scalp are not assigned a dose form of 'scalp application'. Consensus was reached that a dose form of 'pomade' is not required and that the names of the VMPs should continue to specify the products as ointments rather than pomades because this clarifies the basis that is required.
37 | Java plug-in for dm+d browser | NHS RxS | 2015-04-20 | Closed | 2016-03-15 | The dm+d browser provided by the NHSBSA uses a Java plug-in. Recent versions of some web browsers such as Google Chrome block the Java plug-in. The dm+d browser is currently compatible with other web browsers including Internet Explorer and Firefox. Information has been received indicating that most web browsers will stop supporting the use of Java. An alternative for the dm+d browser is likely to be required later in 2015. | 13/05/15 - investigation of options to modify the dm+d browser so that it does not use a Java plug-in have started 13/07/15 - the NHSBSA will change the dm+d browser to use a web application in place of the Java plug-in. 08/10/15 - the new version of the web browser will be made available early November 2015. 22/01/16 - user feedback on the beta version of the modified web browser confirmed that further performance improvements were needed and therefore the new version will not be available until February 2016. 10/02/16 - the performance improvements have been made and the modified web browser will be deployed in February 2016. 15/03/16 - the modified web browser was deployed on 24 February 2016
38 | Use of 'Concentrate' in VMP descriptions to distinguish higher strength products | NHS RxS | 2015-05-05 | Closed | 2016-02-10 | There have been a number of nationally reported issues with the mis-selection of concentrated oxycodone oral liquid and the more commonly used lower strength (10mg/mL and 1mg/mL). It has been noted that the description used in dm+d does not include the word concentrate for the higher strength product such that mis-selection of the two products is a concern. Recent warnings about this have been sent out via the MSO network and raised by the NPA. A number of national reports have also been received by NHS England identifying potential mix up between the two products. | 27/05/15 - The dm+d editorial group has considered this issue previously (2008). They concluded that to resolve the issue a list of products (VMPs) which should have the term ‘concentrate’ used in the descriptions would be required with an evidence based rationale for population. Experts on Patient Safety were asked to compile this list but so far it has not been progressed. The Content Committee will review whether this is still an appropriate solution to this issue. 13/07/15 - a meeting between the dm+d authors and NHS England will be arranged to identify options to support safer prescribing and dispensing of opioid products with a wide range of strengths. 08/10/15 - a proposal to add the term ‘high strength’ to the VMP names of a few selected opioid preparations where a range of strengths is available has been considered by the Content Committee. There are some concerns about the consequences of changing VMP names and the proposal will be discussed further with the issue raisers and the MHRA. 10/02/16 - following further discussion, the issue raisers have understood that dm+d cannot introduce a new term and that they will discuss the possibility of a new standard term with the MHRA, who in turn would need to raise this as a new EDQM term.
41 | Minoxidil foam & Schedule 1 | NHS RxS | 2015-08-13 | Closed | 2015-10-08 | Enquiry from a pharmaceutical advisor as to whether minoxidil foam should have the indicator set to show the VMP is included in Schedule 1 to the NHS (GMS Contracts) (Prescription of Drugs etc.) Regs 2004. The advisor is concerned that the NHSBSA is providing incorrect advice to prescribers. | 21/08/15 - although the corresponding AMP for minoxidil foam is covered by these Regulations, the VMP is not. An NHS prescription for minoxidil foam would therefore be passed for payment by the Pricing Authority (the NHSBSA). 08/10/15 - the authoring team has verified that the indicator is set correctly for this product.
39 | VMP Prescribing Status of fentanyl patches | NHS RxS | 2015-05-08 | Closed | 2015-10-08 | Organisations such as the Care Quality Commission and the UKMI group recommend that fentanyl patches are prescribed by brand name. The issue raiser (a CCG) has received reports of incidents where patients have accidentally applied or been prescribed more than one fentanyl patch if they, their carer or the prescriber does not recognise a branded fentanyl. They are concerned about the potential for overdose and wish to explore whether the dm+d data can be used to support safer prescribing. | 14/05/15 - There are a number of options to support the safe prescribing of fentanyl patches, not all of which involve changes to the dm+d data. One option is to change the VMP Prescribing Status flag from 'valid as a prescribable product' to 'VMP not recommended to prescribe — brands not bioequivalent'. Information in the Summaries of Product Characteristics (SmPC) for fentanyl patches has already been reviewed by the dm+d authoring team because there are statements that would suggest not all fentanyl patches are bioequivalent but this is not clear cut. The dm+d authors have therefore contacted the MHRA to check whether the products have been licensed as being equivalent to the brand leader. The MHRA has indicated that all generic products have demonstrated bioequivalence to one innovator product and therefore it does appear that switching between the innovator and a generic product would pose a negligible risk to public health. However this may not necessarily be the case with switching between generic patches. Caution is therefore generally recommended hence the stated SmPC warning ‘It is not possible to ensure the interchangeability of different makes of fentanyl transdermal patches in individual patients. Therefore, it should be emphasised that patients should not be changed from one make of fentanyl transdermal patches to another without specific counselling on the change from their healthcare professionals’. The dm+d Content Committee will consider whether it is appropriate to change the VMP prescribing status to 'VMP not recommended to prescribe — brands not bioequivalent'. 13/07/15 - possible options will be investigated with the issue raiser to reduce the risk that a patient receives a fentanyl overdose because the prescriber does not recognise that the patient has already been prescribed a fentanyl patch by brand name. 08/10/15 - the issue raiser has confirmed that the issue can be resolved without changing the dm+d data.
29 | Drug categorisation by pharmacological group | HSCIC | 2013-07-15 | Closed | 2015-10-08 | Request to consider the addition of a new data element to the dm+d database - “Pharmacological group” eg Penicillin, Macrolide, B-Blocker, ACE inhibitor etc "This is needed for standardisation of decision support software between suppliers FDB, Ascribe, EMIS etc. If a patient is allergic or intolerant to a pharmacological group then the software needs to have a common SNOMED CT code to cross check each individual drug as it is prescribed." | 16/07/13 - the HSCIC Pharmacy Terminology Team are currently looking into requirements for a new grouper class that will address this issue. System suppliers and clinicians have been asked for feedback and the team has also been in communication with central programmes such as the QOF team and also GP2GP. The GP2GP team intend to drive a project involving all the key system suppliers to define what is required to support interoperability of distinct systems with respect to allergies and adverse reactions. The HSCIC Pharmacy Terminology Team are preparing a proposal around the new grouper class and this will be circulated for feedback. 29/10/13 - Content Committee has requested an update on the proposal around a new grouper class 18/02/14 - HSCIC are proposing a mapping between dm+d and concepts created to align to the British National Formulary down to sub-paragraph level. The new concepts would be part of the SNOMED CT release rather than part of the dm+d data set. This would help facilitate the implementation of dm+d in clinical systems by providing some of the functions of Read codes. The bonus file of ‘pseudo-BNF’ codes provided through TRUD alongside the dm+d extract file could continue. Further development of a pharmacological grouper class will be planned for after the current NICE consultation on the BNF is complete. 14/05/14 - preliminary discussions have taken place with the provider of the BNF; further action is planned for after the current NICE consultation on the BNF is complete. 18/08/14 - NICE has recently published the comments received as part of its consultation on the BNF. These are now being evaluated. 23/12/14 - further discussions have taken place with the provider of the BNF on plans for introducing the new digital BNF. 12/03/15 - The NHSBSA and HSCIC are participating in further discussions with the publishers of the BNF to explore if their changes will support this use case. 13/07/15 - no further update. 08/10/15 - further analysis of the changes to the BNF published in September 2015 confirm that there are no changes for the dm+d data at this stage to support the addition of a new data element for "pharmacological group".
40 | VMPs for testosterone gel | NHS RxS | 2015-07-15 | Closed | 2015-07-31 | The VMP names for products containing testosterone gel do not clearly distinguish between the unit dose tube and the unit dose sachet. Two issue forms have been received where the issue raisers have interpreted the name of the VMP for testosterone gel in a unit dose tube (Testosterone 50mg gel) as covering both dose forms. There are two VMPs (one for unit dose tube and one for unit dose sachet) and each VMP has a single AMP. | 31/07/15 - the two VMP names have been amended to include reference to 'unit dose tube' and 'unit dose sachet'.
23 | Price representation at AMPP level for Part VIIIB specials | NHS RxS | 2012-08-08 | Closed | 2015-06-30 | A pharmacy system supplier would like the prices associated with Part VIIIB specials to be added to the VMPP instead of the AMPP because historically generic prices have been held at the VMPP level on dm+d. The pharmacy system supplier has used a rule that generic prices are held at the VMPP level. The location of Part VIIIB specials prices at the AMPP level causes extra work as a consequence. | 13/09/12 - the prices have been populated on the AMPP for Part VIIIB specials rather than the VMPP to allow the introduction of Part VIIIB without requiring extensive changes to systems at NHSRxS. 29/11/12 - Content Committee agreed that it would be consistent with the dm+d data model to hold the price for Part VIIIIB specials as an attribute on the VMPP rather than on the AMPP for the Drug Tariff Special Order products. Actions required to move the price to the VMPP will be identified. 06/02/13 - the effort required to make this change needs scoping before the Content Committee can determine whether to support the change 23/05/13 - the NHSBSA has begun the appraisal to identify the effort required to progress the change to move price to VMPP for Part VIIIB specials 29/10/13 - the Content Committee has agreed that changes should be made to dm+d to include a new value for the VMPP DT payment category of Part VIIIB. When the likely timescale for implementing the change is known, users will be informed well in advance of the implementation date. Prices will be populated on the VMPPs for Part VIIIB special order products. 18/02/14 - the change to add a new value has yet to be assigned a priority by the NHSBSA and the Department of Health sponsor has been asked to confirm the priority that should be assigned. Prices have been populated on the VMPPs for Part VIIIB special order products. 14/05/14 - further discussion around when the change can be implemented is needed and its relative priority compared to other changes for the NHSBSA needs confirming 18/08/14 - the change to the VMPP Drug Tariff Payment Category will be implemented in 2014/15 by the NHSBSA as part of its next work package. An implementation date has not yet been set. 23/12/14 - no further update. 05/03/15 - The new value for the VMPP DT payment category will be included in the dm+d data from 22 June 2015. 13/07/15 - the new value is included in the dm+d data.
20 | Availability of the monthly Drug Tariff via TRUD | NHS RxS | 2012-08-08 | Closed | 2015-06-30 | A pharmacy system supplier would like the Drug Tariff data to be disseminated in dm+d on the TRUD in the same timescales as the Drug Tariff is provided (i.e. before the 1st of the month); this would enable the data to be downloaded, manipulated and embedded into their systems more easily. Currently they manually populate the information into their system using a hard copy of the Drug Tariff. Data is in the pharmacies as late as 13th of the month (e.g. 1st is a Friday so TRUD is available Fri 8th which they can not access until Mon 11th and then they need time to process and send to the pharmacies). This causes problems as the data is embedded into their system and to support the integrity of the dm+d data they have made certain fields uneditable. | 13/09/12 - explanation given to issue raiser about the difference in purpose and timescales for release of data between the Drug Tariff and dm+d but they reinforced that they would like this issue escalated to the NHS dm+d Content Committee. 29/11/12 - Content Committee requested a paper to consider the issues around release dates for dm+d and whether it would be possible to provide the dm+d data more in line with the Drug Tariff publication cycle. 06/02/13 - no further update 23/05/13 - Content Committee has identified two possible options that may resolve this issue, one option would have a greater impact on all dm+d users and they have therefore requested that the options are discussed with the issue raiser to help inform which one is to be taken forward. 29/10/13 - a teleconference has been arranged to discuss the options with the issue raiser. 18/02/14 - the issue raiser has confirmed that provision of the data outside the dm+d data files would resolve the issue for them and they appreciate the impact changing the dm+d release cycle would have on other users of dm+d. The NHSBSA has agreed to explore the issue further after implementation of changes to the electronic Drug Tariff (second quarter 2014) because this may provide an alternative route for the issue raiser to access the Drug Tariff data more easily. 14/05/14 - no further action required by the NHSBSA until changes to the electronic Drug Tariff are implemented. 18/08/14 - there has been a delay in the implementation of the changes to the electronic Drug Tariff. 23/12/14 - implementation of the changes to the electronic Drug Tariff are expected in February/March 2015. 05/03/15 - changes to the electronic Drug Tariff will be live by 1 April 2015. 08/04/15 - there has been a further short delay to the availability of the revised electronic Drug Tariff. 07/05/15 - the revised electronic Drug Tariff is available. NHS Prescription Services will investigate how it is being used by IT system suppliers to update data. 13/07/15 - The NHSBSA will explore alternative routes (outside dm+d) for the issue raiser to access the Drug Tariff data more easily.
17 | VMP prescribing status of appliances that used to be medicines | NHS RxS | 2012-06-14 | Closed | 2015-06-30 | Editorial Policy states the "Never valid to prescribe as a VMP" prescribing status flag should be applied for an appliance where: "Appliances, dressings and bandages that do not have an official DT specification (or are not fully specified by an EP, BP, BPC monograph) will have a prescribing status of never valid to prescribe as a VMP." There are several appliances e.g. Hydroxypropyl guar 0.2% eye drops in dm+d that used to be medicines and fit the above definition (in having no DT, EP, BP, BPC spec) but have not been flagged as never valid to prescribe as a VMP. According to the Editorial Policy it should have a prescribing status of 'never valid to prescribe' but it has a status of 'valid as a prescribable product'. Does the Editorial Policy need to be clarified to allow devices that used to be medicines to have a prescribable VMP, or is it just that the Policy has not been implemented properly? | 14/06/12 - investigation begun 19/09/12 - VMPs have been identified where the VMP is indicated as valid to prescribe but where there is no specification (the VMP for Hydroxypropyl guar 0.2% eye drops has already been changed). The reasons for the VMP being indicated as valid to prescribe are being analysed and information will be made available to the Content Committee to decide whether a change in editorial policy is necessary. 29/11/12 - The Content Committee considered that strict application of the editorial policy for assigning the prescribing status of VMPs that are appliances, dressings and bandages may not be appropriate for some VMPs that do not have a formal specification (Drug Tariff, EP, BP, BPC). For some of these VMPs, setting the prescribing status to valid to prescribe as a VMP (i.e. by generic name) would reflect existing prescribing practice. The editorial policy will therefore be reviewed to identify which appliances, dressings and bandages could safely be prescribed using the VMP description. 06/02/13 - A proposal to amend the editorial policy has been considered by the Content Committee. They have requested further information about the 'specifications' used by the MHRA for the regulation of medical devices before deciding whether to amend the policy. 23/05/13 - The MHRA considers that it is difficult to compare products with marketing authorisations and medical devices in terms of standards because they are subject to different regulations. Medical devices that contain single ingredients do not have to comply with the BP or EP and there is no naming hierarchy for devices in the same way as with generic naming of medicines. The Content Committee therefore does not consider it appropriate to set the prescribing status of these devices to valid to prescribe as a VMP. They have requested exploration of whether a status of ‘not recommended to prescribe’ should be applied to the VMPs for these medical devices with a new value to explain why generic prescribing is not appropriate. 29/10/13 - the Content Committee has recommended that a change is made to the dm+d to include a new value for the VMP prescribing status of ‘VMP not recommended to prescribe – no Drug Tariff specification’. This value will be used for appliances, dressings and bandages that use an approved non-proprietary name but do not have an official Drug Tariff specification. Sufficient notice of the change in policy and the subsequent changes to the extract files will be given to users of dm+d before changes are implemented. An implementation date has not yet been agreed. 18/02/14 - this change has yet to be assigned a priority by the NHSBSA and the Department of Health sponsor has been asked to confirm the priority that should be assigned. 14/05/14 - further discussion around when the change can be implemented is needed and its relative priority compared to other changes for the NHSBSA needs confirming. 18/08/14 - the change to the VMP prescribing status will be implemented in 2014/15 by the NHSBSA as part of its next work package. An implementation date has not yet been set. 23/12/14 - no further update. 05/03/15 - The new value for the VMP prescribing status will be included in the dm+d data from 22 June 2015. 13/07/15 - the new value is included in dm+d.
16 | Wholesaler (Outer) packs | NHS RxS | 2012-05-21 | Closed | 2015-06-30 | Pharmacy systems are increasingly being built to use dm+d as the terminology of choice to support the coding of medicines and medicine packs. As such it could be seen as desirable that the number of non-dm+d codes are reduced to reduce the risks of using multiple coding systems. Currently dm+d does not contain wholesaler packs ('outers'). The outer pack is normally the only pack that is available in the supply chain between the wholesaler and the pharmacy. The inability of the pharmacy system to use dm+d codes to represent these packs is preventing the use of dm+d for accurate stock control and for ordering from wholesalers. Many if not all of these packs represent two or more existing dm+d packs wrapped together by the manufacturer for the purpose of wholesaling e.g. 10 x 30 sachets. Many of these wholesaler packs also contain a barcode that can be scanned and the product quickly added to stock. Addition of wholesaler packs would increase the ease with which dm+d can be implemented in pharmacy (and wholesaler) systems. Should the dm+d use cases be changed to support stock control and ordering? | 19/09/12 - the Content Committee will be asked to consider whether inclusion of 'outer packs' used in the supply chain forms part of the dispensing use case and the impact including 'outer packs' would have on the other use cases. 29/11/12 - The Content Committee considered that this type of pack could possibly fit the dm+d data model but would require some change e.g. to attributes that support the reimbursement use case. This issue is to be considered further by the Content Committee. 06/02/13 - no further update 23/05/13 - no further update 29/10/13 - the Content Committee has decided to seek dm+d users' views as to whether the use cases should be expanded to support pharmacy systems ordering from wholesalers. A consultation paper will be prepared. 18/02/14 - input from the Commercial Medicines Unit has been sought. The CMU’s view is that the single NHS GS1 data pool that is to be created for use in NHS systems should provide the data that dm+d users require for interactions with the supply chain. The Department of Health has set out actions for the development of national and local infrastructure to support the adoption of GS1, as the supply chain coding standard. A diagram is required to illustrate the relationship between dm+d and the NHS GS1 data pool. This will help inform whether changes to the dm+d data are required. 14/05/14 - An NHS eProcurement Strategy has been published in April 2014 that recommends extending the use of eProcurement solutions, together with the adoption of global standards (GS1). The European Commission’s Falsified Medicines Directive will also address how coding standards are used to identify medicines within the supply chain. The Content Committee will monitor the development of the GS1 NHS data pool to assess if this resolves the issue. 18/08/14 - too early to assess whether the development of the GS1 NHS data pool will resolve the issue. The potential impact of the Falsified Medicines Directive is also not yet known. 23/12/14 - an update from the CMU on progress with creating the GS1 NHS data pool will be sought. 12/03/15 - the GS1 NHS data pool has yet to be procured. It will initially be accessed only by secondary care users. The Content Committee will continue to monitor how the implementation of the eProcurement Strategy may impact dm+d. 13/07/15 - the GS1 NHS data pool will hold the data on products and packs available in the supply chain. The dm+d data will interface with the data pool at the level of the actual medicinal product pack through the GTIN code that will be part of both data sets. The dm+d use cases therefore do not need to support stock control and ordering.
31 | Expression of morphine sulfate 20mg/ml oral solution sugar free (Oramorph 20mg/ml concentrated oral solution) | NHS RxS | 2013-12-23 | Closed | 2014-12-23 | There are examples of morphine sulfate oral solutions on dm+d as either strength/5ml or strength/ml. This has the potential to cause confusion. A pharmaceutical advisor believes this has resulted in an incident in their locality | 24/12/13 - replied to the enquirer explaining when oral solutions/suspensions are expressed on dm+d as /5ml or as /ml. Informed them that these descriptions have been on dm+d for 10 years but that the enquiry would be discussed with peers to consider further. 18/02/14 - the issue raiser will be asked to confirm if they have raised the issue with Patient Safety at NHS England and advised to do so. The issue will then be discussed further with Patient Safety. 14/05/14 - the issue raiser will be contacted again to seek confirmation that this has been notified to NHS England as a patient safety incident. 18/08/14 - the issue raiser has confirmed that this incident has been notified through the National Learning & Reporting System. Very few reports of similar incidents have been received, however under reporting is possible. Further data will be gathered through the Medication Safety Officers. The dm+d is only likely to change the expression of strength if concerted action is agreed with agencies such as the MHRA. 23/12/14 - NHS England has sought further information but there is insufficient evidence to suggest that errors relating to the expression of strength of this product are other than rare.
33 | Difficulty in using dm+d browser | NHS RxS | 2014-02-13 | Closed | 2014-08-14 | Some users are experiencing a problem when trying to access the dm+d browser in that the search box does not appear so the data can not be browsed | 13/02/14 - the latest version of JAVA is incompatible with the dm+d browser and there is a change required at the NHSBSA to authorise the JAVA software through the purchase of a Code Signing Certificate (Applet). Options to access the browser in the interim are to: lower the security settings on the pc, use an alternative web browser such as firefox, or to revert back to the previous version of JAVA. Another option is to use one of the alternative dm+d browsers that are not endorsed by the dm+d. 14/05/14 - the NHSBSA will purchase a Code Signing Certificate. 14/08/14 - the dm+d browser is compatible again with all versions of Java.
30 | Usability of the form for raising issues | HSCIC | 2013-05-29 | Closed | 2014-05-14 | The form used to raise issues with dm+d is not user friendly to complete and it is unclear who should fill in which fields. Information about the issue raiser is not included on the form. The process of raising an issue is not well explained on the web site. | 31/05/13 - clarified with issue raiser when the issues from should be completed and when it is more appropriate to send in an enquiry. This clarification has been added to the dm+d web page 'general enquiries and issues'. The form for raising an issue will be redesigned. 29/10/13 - Content Committee has recommended that the form for raising issues is redesigned 18/02/14 - Content Committee has approved the redesigned form and this will be available through the dm+d web site 14/05/14 - the redesigned form is now available on the dm+d web site
15 | Naming of amino acids | NHS RxS | 2012-03-19 | Closed | 2014-05-14 | Inconsistencies have been identified in how amino acids are named in dm+d in relation to whether the name identifies the stereoisomer. This has resulted in the inclusion of duplicate concepts eg l-cystine and cystine are both ingredients in dm+d | 02/04/12 - options for naming amino acids under investigation, this may require changes to editorial policy and a significant number of invalidations 23/04/12 - issues with using the rINN to name amino acids are being identified 19/09/12 - summary of issues prepared for Content Committee to consider whether wider consultation is required to amend the editorial policy 29/11/12 - no further update 06/02/13 - Content Committee approved a change to the current editorial policy that will allow a modified name to be used in preference to an approved name for the naming of amino acids (and monosaccharides) in dm+d. The authoring teams will identify all primary care and secondary care products that require invalidation and reauthoring, and a date for implementation of the change including a notice period will be communicated to dm+d users. 23/05/13 - The revised editorial policy is ready and will be released to dm+d users as part of the next version of the editorial policy (following ISB approval). Plans are in place to identify the VTMs, VMPs, VMPPs and ingredients that require re-authoring. 29/10/13 - identification of VTMs, VMPs, VMPPs and ingredients that require re-authoring is nearly complete. Changes in data will be evident for dm+d users from January 2014 and will be completed in a number of phases until March 2014. Users will be informed about each set of changes using the TRUD communication. 18/02/14 - nearly all the data changes have been made and the work is on target to complete by March 2014. 14/05/14 - all data changes have been completed
5 | GTIN codes | NHS RxS | 2010-12-01 | Closed | 2014-02-18 | GTIN codes are provided as a bonus file and are not formally part of dm+d. They are therefore not visible in the browser. Only 21% of AMPPs are populated with a GTIN code. Some AMPPs have more than one GTIN code. There is no mechanism to verify GTIN codes. Coding for Success recommended that dm+d is the source for GTIN codes for NHS use. Secondary care procurement and automated dispensing systems would find GTIN codes very useful and we have been asked to consider including more GTIN codes. | 14/03/11 - further exploration of whether GTIN codes can be brought fully within the dm+d structure has been requested and a proposal will be made to Content Committee. 05/07/11 - paper to go out for consultation before end July 11. The Peer Review Panel is not yet in place and therefore comments will be requested via the UKTC IF. 05/10/11 - feedback discussed at Content Committee meeting. Support for the principle of expanding GTIN code population in dm+d, issues with population and validation of codes need to be investigated in more detail. 10/01/12 - further investigations are ongoing into population and validation of GTIN codes 11/04/12 - summary of issues prepared for Content Committee 23/04/12 - an appendix to the editorial policy for the population of GTIN codes will be prepared (taking into account the responses to the consultation paper) and further actions to progress the availability of GTIN codes in dm+d will be identified. 12/07/12 - draft editorial policy reviewed at Content Committee meeting - to be updated. Actions to include GTIN codes in dm+d in line with the policy identified. An implementation timeline is being drafted. Sufficient notice of the change in policy and the subsequent changes to the extract files will be given to users of dm+d before changes are implemented. 29/11/12 - Content Committee have approved the appendix to the editorial policy for GTINs. Actions to implement the policy are progressing but no date has yet been agreed to change the files. 06/02/13 - the change to the NHSBSA’s systems to allow delivery of the editorial policy for GTINs has been given a higher priority and work has started to confirm which resources are required to make the changes. 23/05/13 - A business case to make the changes at the NHSBSA has been approved and a project initiated. The detailed requirements are currently being documented. Users will receive notification at least 3 months in advance of the change to the TRUD files. Earliest date for implementation is November 2013. 29/10/13 - the changes being made to dm+d to formally include GTINs are progressing well. Users of dm+d have been advised that the changes will be evident in the dm+d extract available Monday 2 December 2013. 18/02/14 - changes to dm+d complete and signed off by Content Committee.
32 | BNF bonus file | NHS RxS | 2014-01-02 | Closed | 2014-02-18 | Request from the UK Terminology Centre Implementation Forum to consider moving the file of 'BNF' codes from the bonus file to the main dm+d files | 09/01/14 - the bonus file provides details of both BNF and ATC information relating to VMPs and AMPs. The BNF data is based on codes assigned by the NHSBSA for use in their information systems and has not been formally recognised by the BNF. The inclusion of a pharmacological grouper class based on the BNF is being considered (see issue 29). 18/02/14 - this issue is being progressed as part of issue 29 and the bonus file containing the pseudo-BNF codes does not need to become a formal part of dm+d at this point.
26 | Blood products | HSCIC | 2013-05-24 | Closed | 2013-10-29 | dm+d does not embed blood products such as 1. Cryoprecipitate 2. Fresh Frozen Plasma 3. Packed Red cells 4. Platelets These are needed for clinical decision support in eprescribing and administration systems, in use in the acute trusts. | 30/5/13 - representation of blood and blood components is outside the current scope of dm+d. Secondary care users are expected to use SNOMED CT to provide this potentially diverse content. However the content in SNOMED CT may not be sufficient to provide all the potential concepts required for the prescribing of blood and blood components in the UK. HSCIC have been working with NHS Blood and Transplant and ICCBBA (www.iccbba.org/) to produce a model for the representation of blood products in SNOMED CT. Since our proposals are based on the ISBT128 terminology there are some issues of Intellectual property to resolve. It is likely to take some time before the politics and the model are agreed so that additional content can be added to SNOMED CT. However it is likely that the prescribing of blood and blood components will remain outside of the scope of dm+d.
27 | Inhaled medicines & delivered doses | NHS RxS | 2013-05-30 | Closed | 2013-10-29 | The British Pharmacopoeia (BP) has recommended that: a) Terminology should be aligned with the Ph. Eur. for the naming of inhalation dosage forms and test methods. b) The BP ‘Preparations for Inhalation of the British Pharmacopoeia’ general monograph and individual inhalation product monographs should be aligned with the Ph. Eur. ‘Preparations for Inhalation’ general monograph (0671). c) The dose (and its limits) should be stated in terms of the Delivered Dose. This will result in changes to product descriptions in dm+d and may affect which AMPs are linked to which VMPs. | 05/06/13 - impact analysis started by authoring teams 01/07/13 - initial analysis indicates there are already some differences between licensed products and their delivered dose, but not their metered dose. Further investigation required as to whether these products are clinically equivalent and the impact this will have on linking AMPs to VMPs. The MHRA will be asked about how they would expect to see the name (including strength) expressed on the SPC and packaging and whether this will be in terms of the metered dose or delivered dose (or both). 29/10/13 - the MHRA confirmed that for established products (metered dose inhalers) strengths can continue to be expressed as the metered dose on the label; section 2 of the Summary of Product Characteristics includes the equivalent delivered dose to the metered dose. For newly approved brands of established products the dose will also be expressed in both ways in the SPC. For new active substances (where there are no brands already on the market) the dose will be expressed as the delivered dose on the product label. Although within Europe there will eventually be a move to using just the delivered dose, no time line has been agreed for when this must be implemented. There does not need to be a change in dm+d currently to the description of products where the strength is expressed as the metered dose.
28 | Flavour not specified' AMPs for flavoured nutritional products | HSCIC | 2013-07-03 | Closed | 2013-10-29 | Prescribing and dispensing System Suppliers are getting many queries because of the dm+d descriptions for borderline substances such as: Ensure Plus Crème (Flavour Not specified). This has been added as an ‘Actual Medicinal Product’ (AMP), but it clearly is not a real product that you can take off the shelf and used so it is not a true AMP. This product does not have any packs connected to it either, causing problems for dispensing. Please can this be reviewed again and consider either: dm+d make the ‘flavour not specified’ AMP’s obsolete OR link to AMPP’s | 04/07/13 - discussed with issue raiser that it would be useful to understand what types of queries are being generated and the extent to which their customers are experiencing problems. However the issue raiser is unwilling to provide specific information. The EPS team will also be asked if they have been advised of any system suppliers experiencing similar issues. 29/10/13 - the issue raiser has been unable to provide specific information as to the types of problems their customers are experiencing. The Electronic Prescription Service has not received feedback from their users that these AMPs are causing issues with electronic prescriptions.
21 | Scotland Drug Tariff | NHS RxS | 2012-08-08 | Closed | 2013-02-06 | A pharmacy system supplier has systems interfacing with the NHS outside England. They would like dm+d data to include Scotland Drug Tariff data so that they can link and map the content of dm+d and tailor it to the Scottish dispensing health care use case. | 13/09/12 - although dm+d primarily has a focus on NHS England this issue will be escalated to the Content Committee. 29/11/12 - NHS Scotland has also requested closer liaison because the dm+d is used in Scotland to underpin medication initiatives. Content Committee agreed in principle that a formal collaboration with NHS Scotland can be explored.
22 | Removal of price on discontinued AMPPs | NHS RxS | 2012-08-08 | Closed | 2013-02-06 | A pharmacy system supplier would like indicative prices to remain on discontinued generic AMPPs for ideally up to 2 years because stock may remain in dispensaries for this duration. | 13/09/12 - the procedure followed at NHSRxS for removal of prices is as follows: the indicative price is left on a discontinued proprietary AMPP but on a generic AMPP it is removed 3 months after the discontinuation date. The reason for this is that some users have been confused about the availability of a discontinued generic AMPP because of the presence of a price. 29/11/12 - options for how long indicative prices are left on discontinued products will be identified and a proposal will be submitted to Content Committee. 06/02/13 - the Content Committee determined that the price should be set to 0 rather than retaining the indicative price.
24 | BNF Codes | NHS RxS | 2012-08-08 | Closed | 2013-01-08 | A pharmacy system supplier would like dm+d to contain pseudo-BNF codes on dm+d. Currently these codes are manually populated onto their database by their staff. They use the pseudo-BNF codes when reporting/discussing PACT data to customers. Also BNF codes would be useful to them in reporting on prescribing and dispensing therapeutic group analysis. Inclusion of pseudo-BNF codes in dm+d would enable a map of BNF codes to SNOMED codes. | 13/09/12 - the BNF codes are outside the governance arrangements in dm+d and hence they are located in bonus files rather than core dm+d files. The codes in the BNF bonus files do not provide full coverage of all products; for example they are only added to products included in the BNF main chapters and have not been populated on all products historically. The codes are pseudo-BNF codes because they have been created by the NHSBSA and are not endorsed by the Joint Formulary Committee. Further discussions are needed as to whether it is appropriate for the BNF codes to be brought within the scope of the ISB standard. 29/11/12 - the ‘BNF’ codes are outside the governance arrangements in dm+d and hence they are located in bonus files rather than core dm+d files. Although these ‘BNF’ codes are widely used e.g. in NHS RxS’s prescribing and dispensing information systems, they are not formally recognised by the British National Formulary. The codes are an extension of the chapters and sections used by the BNF to categorise information. Content Committee has agreed that it is not appropriate to bring the ‘BNF’ codes within scope of the Information Standard for dm+d.
25 | VMP names differ from names in BNF | NHSRxS | 2012-10-22 | Closed | 2013-01-08 | There are various reference sources for the description of medicines and none of them seem to be able to agree a unified editorial policy. For example they differ in whether the salt is included or not in the name. An NHS Trust uses one drug database for prescribing and a different drug database for dispensing. Obviously, any discrepancy between the two will trigger questions like “why is it described with the salt for prescribing and yet without the salt for dispensing?”. The issue raiser would like to recommend that the dm+d create another new field called “BNF generic name” - which would exactly match the BNF medication description. He has suggested that e-Prescribing suppliers and pharmacy dispensing suppliers could then liaise with their software users and decide to use the dm+d “Name” description or the newly proposed “BNF generic name”. | 29/11/12 - Content Committee consider that the introduction of an option to use different names would be incompatible with the status of dm+d as the recognised Information Standard for the NHS. The dm+d Name should be used wherever data are exchanged between clinical systems.
13 | Limitation on field length of dose forms | NHSCFH | 2011-08-18 | Closed | 2012-11-29 | There is a 60 character limitation to the field length for dose forms on the NHSRxS database that supports dm+d and there are wider XML issues with a longer field. The EDQM has introduced combined terms for dose forms that are longer than 60 characters eg 'powder and solvent for prolonged release suspension for injection' which is 65 characters including spaces. | 10/01/12 - Content Committee requested that the two options for resolving the issue be documented and then taken for wider consultation. The options are to either increase the field length of dose forms or introduce abbreviations into the description of the dose form. 19/09/12 - there are currently no products that have a dose form that exceeds the limit on the number of characters and this issue has been given a lower priority to resolve 29/11/12 - Content Committee concluded that this is a risk that should be monitored rather than issue to be resolved. The issue can be re-opened if products are identified in future where the dose form is longer than 65 characters.
18 | VMPs with similar names that raise safety concerns | NHSCfH | 2012-08-21 | Closed | 2012-11-29 | Users of dm+d have expressed concern that the names of some VMPs are similar which increases the risk of errors in prescribing and dispensing. The specifc example raised is Clobetasone 0.05% cream and Clobetasol 0.05% cream. The National Vision User Group have held discussions with NHS Scotland who have raised a formal clinical safety alert. Dm+d descriptions may be printed, read and used for dispensing or administration purposes without software support and, as dm+d codes and descriptors are used in diverse messaging and application implementations, it is impossible for each and every implementer to incorporate a standard, trustworthy method of highlighting the risk. Changing the displayed descriptor in software applications using native dm+d would be in conflict with the intentions of a standardised drug dictionary tool, and is of course risky where messaging standards in ePrescribing applications are mandating dm+d. National Vision User Group have therefore requested that consideration is given to changing the VTM descriptions of these items (and thus propogating to VMP / AMPs) as follows: clobetasone to clobetasone butyrate and clobetasol to clobetasol propionate. | 21/08/12 - similar drug names is a long standing concern for patient safety. The issue raiser has suggested changing the names to indicate clobetasone butyrate or clobetasol propionate in dm+d but this would be outside editorial policy and would not resolve the issue for other products. CFH have asked the NPSA for their view. The issue has been raised by ISD Scotland to the Clinical Safety Team at NHS CFH. NHS Scotland has issued a safety alert recommending prescribing the clobetasone and clobetasol products by brand name. 22/08/12 – Meeting of representatives of the CFH clinical safety team, EPS and dm+d agreed that the requested change to terms in dm+d would only patch a bigger issue of lookalike/soundalike names that require a central policy for representation. The agreed response to the raisers of the issue would be that the clinical safety team did not support the issue as raised and would not be requesting a change in dm+d. (dm+d issue recommended closed). However there was agreement that the bigger issue of lookalike/soundalike names needs addressing. To this end a meeting has been called for October 11th with representatives from the clinical safety team, dm+d (CFH and BSA), EPS, NPSA, CUI and Charles Gutteridge. Any recommendations from this meeting that may impact on dm+d will be brought to the dm+d Content Committee for discussion.
19 | Workload in complying with the dm+d ISB Standard (ISB 0052) | NHSCFH | 2012-08-23 | Closed | 2012-11-29 | There will be a very significant workload for all parties and failure to attain the desired goal within the time frame will cause hospitals and clinical system suppliers to breach the ISB requirement. ISB 0052 requires all UK clinical systems to be compliant with NHS dm+d by 2017. The issue raiser has assumed that in order for NHS & non-NHS hospitals to comply with this ISB, the dm+d dataset must incorporate all of the commercial unlicensed, aseptic & non-aseptic hospital commercial & locally manufactured products and aseptic and non-aseptic extemporaneously dispensed products used by hospitals on a daily basis. | 02/09/12 - the issue was based on the premise that secondary care users wouldn’t be able to comply within the requisite timescales as dm+d doesn’t contain all the specials and unlicensed medicines that are used in secondary care. The summary of the response given was that the Standard is limited to licensed medicines in dm+d therefore unlicensed medicines not in dm+d are out of scope of the Standard. However notwithstanding this fact our main aim is to make dm+d usable across secondary care, not just mandating and forcing the Service to be compliant with the Standard. To this end we are currently working to increase the coverage of unlicensed medicines in dm+d to increase usability.
14 | VTMs for liposomal formulations and albumin-bound formulations | NHSCFH | 2012-02-07 | Closed | 2012-09-17 | Doxorubicin is available in 3 formulations for which there are currently 2 VTM concepts. Doxorubicin hydrochloride powder for solution for injection & solution for injection map to the VTM doxorubicin hydrochloride but the 2 liposomal formulations map to the single VTM doxorubicin liposomal (product). Doxorubicin encapsulated in liposomes (brand Caelyx) & doxorubicin citrate liposomal complex (brand Myocet) are not bioequivalent & the constituents of the liposomal complexes are different in each formulation. Similar differences apply to parenteral formulations of amphotericin where the single VTM amphotericin (lipid formulation) maps to Ambisome & Abelcet. These can be distinguished as amphotericin liposomal powder for solution for infusion & amphotericin lipid complex concentrate & are significantly different in terms of their bioavailability. These can be distinguished as amphotericin liposomal powder for solution for infusion and amphotericin lipid complex concentrate and are significantly different in terms of their bioavailability. The plain powder for solution for injection (Fungizone) correctly maps to Amphotericin (product) at VTM level. In each of these cases the nature of the active ingredient complexes administered to the patient is significantly different. The products are not interchangeable, & great care has to be taken to ensure that the patient receives the appropriate product. In order to distinguish clearly between the available product, separate VTM in each case for the different liposomal/lipid bound active ingredients is recommended. A similar issue arises with paclitaxel albumin-bound as the bioavailability is different from that of the non-albumin bound material & perhaps this case could be considered at the same time. | 09/03/12 Description of liposomal products and albumin bound formulations is being investigated 05/04/12 Evidence supports the creation of a separate VTM (and linked products and packs) for pegylated formulations of liposomal doxorubicin. Other pegylated formulations have separate VTMs. The VTM will be reauthored in line with the evidence. 11/04/12 - amphotericin VTMs under investigation. New VTM for paclitaxel had been created before issue was logged. 23/04/12 - further expert opinion will be obtained on the VTM for lipid formulations of amphotericin 13/08/12 - VTM for lipid formulations of amphotericin to be invalidated (and linked products and packs) and separate VTMs created to distinguish the active ingredient complexes. 17/09/12 - all changes complete
1 | Unflavoured VMPs for flavoured AMPs | NHS CFH | 2010-05-17 | Closed | 2012-08-02 | Request from EPS Programme to improve mapping of flavoured products between GP systems and dm+d. Some drugs and foods cannot be mapped and therefore system suppliers have requested individual VMPs. Lack of mapping prevents electronic prescribing and is perceived to hinder roll out of EPS. | 17/05/10 - outstanding foodstuffs to be reauthored where there is an appropriate VMP as per editorial policy. Where VMP has multiple brands attached – impact assessment is required. The addition of an unflavoured VMP for medicinal products with flavours requires separate impact assessment. 06/12/10 - foodstuffs with single VMP reauthored. Proposal to invalidate VMPs for foods with multiple brands (those with group VMP based on Drug Tariff heading) and replace with unflavoured, branded VMPs was rejected. An alternative proposal to add an unflavoured AMP is to be evaluated. Content Committee decided that requested change re flavour should not be applied to medicines. 14/03/11 - agreement in principle to add unflavoured AMP concepts to flavoured food products. The Peer Review panel and users signed up to TRUD are to be asked for their views to determine full impact of change. Comments on the proposals to joyce.delarue@nhs.net before close of business on 13th May 2011 05/07/11 - most of the feedback supports the proposal to introduce unflavoured AMP concepts. Food supplement concepts with either a Drug Tariff derived VMP or where the VMP is marked as never valid to prescribe will have AMPs and AMPPs authored that do not specify a flavour. These AMPs will be authored with a single supplier that indicates there is no specific supplier eg ‘Unspecified supplier’. The AMPPs will not have an indicative price. A minimum of 3 months notice of the change will be given to dm+d users via the TRUD communications. Rules for endorsing prescriptions to indicate the flavours prescribed will need to be reviewed before unflavoured AMPs can be authored. 10/01/12 - further investigation has shown that this change can probably be introduced without amending the rules for reimbursing prescriptions. 11/04/12 - change to be made 1 August 2012, TRUD communication to be sent 30 April 2012 30/04/12 - TRUD communication disseminated 02/08/12 - changes made, these will be disseminated in the first dm+d extract in August (6 Aug).
7 | Population of adrenaline concepts | NHSRxS | 2011-01-07 | Closed | 2012-03-09 | For several years NHS dm+d has incorrectly described products supplied by UCB, representing them as the acid tartrate salt rather than the hydrochloride salt. Upon further investigation there seems to be a lack of clarity in the British Pharmacopoeia because different monographs exist for adrenaline with varying profiles with respect to specific salt reference. The issue is whether all adrenaline VMPs and adrenaline strengths should ideally be described in terms of adrenaline only rather than the salt. Any amendments and update to the NHS dm+d is therefore likely to involve invalidation of concepts. Coupled with this, work is being done (upon request of the Content Committee) to revisit how strengths and basis of substance strengths are populated on dm+d. This overlaps with any changes that may be made to resolve this issue. In view of the fact that it is essential that any update to do with adrenaline is accurate and correct, these two activities are not mutually exclusive and need to be done in tandem. | 05/07/11 - A paper has been prepared to request feedback on whether editorial policy should be amended. Peer Review Panel is yet to be established and therefore the Content Committee agreed that the paper should be sent to members of the UKTC IF for feedback. The MHRA is discussing the naming of adrenaline products which will include whether the salt is included in the name. Content Committee has requested an update on the current situation and whether there are further issues to be addressed. 05/10/11 - MHRA advice is that adrenaline should be expressed as the base. Content Committee has requested a paper outlining how adrenaline concepts may be re-authored using the same approach as for noradrenaline. Further consultation via UKTC IF is not required. 10/01/12 - The Committee agreed with the proposal to describe adrenaline products consistently using the “base” as the product concentration within the unit dose at VMP and AMP levels (where non-proprietary names are used). Change to descriptions to be implemented following 6 weeks notice to users of dm+d. 09/03/12 - TRUD communication sent out and changes to be made in dm+d
12 | Population of caffeine concepts | NHSRxS | 2011-11-25 | Closed | 2012-03-09 | There is a long standing question over the population of caffeine. Concern has been expressed that populating in accordance with the editorial policy does not provide clarity as to the basis of the strength ie whether the strength needs to be shown in terms of both the base and the salt. The BNF for Children recommends to always state the dose in terms of caffeine base (Caffeine base 1 mg = Caffeine citrate 2 mg). | 10/01/12 - Content Committee agreed to amend the description of the VMPs for caffeine to include “(base)” in a similar way to noradrenaline and adrenaline. Change to descriptions to be implemented following 6 weeks notice to users of dm+d. 09/03/12 - TRUD communication sent out and changes made in dm+d
4 | Mistletoe extracts | NHS RxS | 2010-09-16 | Closed | 2011-08-18 | The current VMPs for mistletoe extracts are insufficiently granular to allow decision support to be applied to these products. What we have now is a number of VMPs that identify the ingredient and form but not the strength. This means that AMPs attached to a single VMP may differ in strength by a factor of over 1000. Request from secondary care for decision support is that the VMPs are re-authored as for any other medicinal product i.e. drug, strength and form at both VMP and AMP level with the appropriate coded information being added. | 14/03/11 - agreement in principle to reauthor VMPs for mistletoe extracts so that there is 1 VMP for each strength of the existing VMPs and flag the new VMPs as “invalid to prescribe in NHS primary care”. The Peer Review panel and users signed up to TRUD are to be asked for their views to determine full impact of change. 05/07/11 - respondents were in favour of the concepts being reauthored so that there is 1 VMP for each strength of the existing VMPs. The mistletoe extract VMPs are to be reauthored and flagged as VMP not recommended to prescribe – brands not bioequivalent. Advance notification of the change is to be given for users via TRUD communications 18/08/11 - TRUD communication sent out and changes made in dm+d
8 | NCSO & additional concessionary price status | NHSRxS | 2011-04-06 | Closed | 2011-08-01 | When a Drug Tariff concessionary price is agreed (this sometimes occurs when a product has had NCSO status), the VMPP indicative price remains unchanged and reflects the price published in the Drug Tariff. Should the VMPP indicative price be updated even if this price change is announced mid-month? A multiple pharmacy uses this price in certain processes and their Head office data processing system holds this attribute as read only, therefore they cannot currently amend the price. | 05/07/11 - Content Committee has confirmed that the indicative price on dm+d should be the manufacturer/supplier's list price August 2011 - Issue raiser contacted with explanation.
9 | Addition of clinical trial VTMs for decision support | NHSRxS | 2011-05-10 | Closed | 2011-07-28 | The UKTC IF have asked if the VTMs alone could be populated on dm+d for medicinal products used in primary / secondary care that do not yet have a marketing authorisation or are currently in clinical trials. The use case is to support the recording of allergies and adverse reactions to medicinal products and subsequent generation of decision support. Proposed information for population includes www.ukmi.nhs.uk/applications/ndo/default.asp and end user requests. Any VTMs added would need to meet current Editorial Policy for naming VTMs but would not require links to a VMP. The Editorial Policy already covers investigational medicinal products however no products have been added to dm+d. | 05/07/11 - the Editorial Policy covers investigational medicinal products. However no companies have yet submitted products for inclusion. Products are included in dm+d when there is evidence to show they will be prescribed.VTMs will not be populated for clinical trial products without receiving data from the supplier. 28/07/11 - Feedback to be given to UKTC IF members at their next meeting
10 | Indication of release time for VMPs eg for modified release | NHSRxS | 2011-06-13 | Closed | 2011-07-28 | The VMP name does not distinguish between different release periods. Examples include morphine modified release preparations eg 12 hour and 24 hour and once weekly or twice weekly oestradiol patches. Concern has been raised that this is an issue for patient safety in that a patient may receive the wrong product when the VMP is prescribed unless the dispenser can confirm which is required. | 05/07/11 - Content Committee has confirmed that the release time will not be included in the VMP name unless there is a pharmacopoeial standard for duration of action for modified release products. 28/07/11 - issue raiser agreed to close
11 | Differences in VMPs indicated as not recommended to prescribe between dm+d and UKMi | NHSRxS | 2011-06-15 | Closed | 2011-07-28 | The editorial policy for dm+d is not consistent with the UKMi's list of medicines which should be considered for brand name prescribing in primary care. A concern has been raised that there could be medico-legal complications if a pharmacist dispenses the wrong product. | 05/07/11 - Content Committee has confirmed that the editorial policy does not need amending. The indication of a VMP as ‘not recommended to prescribe – brands not bioequivalent’ is determined by whether the BNF or Summary of Product Characteristics (SPC) recommends prescribing by a brand name. 28/07/11 - Issue raiser contacted with explanation.
2 | Container type mapping | NHS CFH | 2010-05-17 | Closed | 2011-06-27 | Request from EPS Programme to improve mapping of products between GP systems and dm+d due to differences in container types. Lack of mapping prevents electronic prescribing and is perceived to hinder roll out of EPS. | Update 17/05/10 - issues need exploring further Update 06/12/10 - paper to Content Committee, Option 2 was accepted (no change to dm+d container types); when new UOM required in dm+d reference should be made to the container types in EDQM. Update 14/03/11 - EPS Programme will be asked to confirm whether issue is resolved Update 27/06/11 - confirmed OK to close as no response
3 | Risk share scheme price | NHS RxS | 2010-07-03 | Closed | 2011-03-14 | Request from Merck Serono to publish the NHS list price in addition to the risk share scheme price in dm+d. Their Rebif products are unusual in that the NHS reimbursement price (the RSS price) is not the same as the company's list price. | Update 14/03/11 - decision is that the indicative price should be the manufacturer’s list price for drugs in the risk sharing scheme. Currently the indicative price for the Rebif products is the NHS primary care reimbursement price.
6 | Appliances & ACBS status | NHS RxS | 2011-01-11 | Closed | 2011-03-14 | Current technical specification does not include population of ACBS status for medical devices. Originally no devices were included in Drug Tariff Part XV. A request has been received to flag a medical device as in the ACBS list. | Update 14/03/11 - ACBS status does not apply to medical devices listed in Part IX of the Drug Tariff and therefore it would be inappropriate to flag medical devices as ACBS approved. System supplier who raised issue to be updated on outcome.
34 | VMP prescribing status of oral mesalazine products | NHS RxS | 2014-02-20 | closed | 2017-11-01 | The issue raiser is recommending that oral mesalazine is not prescribed as a VMP because of the BNF note that states: 'The delivery characteristics of oral mesalazine preparations may vary; these preparations should not be considered interchangeable'. He would like a review of the editorial policy for populating the VMP Prescribing Status with respect to BRAND name vs GENERIC name prescribing and he is proposing that there should be an open forum to discuss the issue. He would like the review to cover how the dm+d best interprets this information and how best to present this information to prescribers and dispensers. He has a preference for which information source should be used. | 02/02/14 - advised the enquirer that this has previously been discussed by the dm+d Content Committee and that the BNF does not unambiguously state that 'prescribers should prescribe by brand' for oral mesalazine products. The issue will be discussed further by the Content Committee at its next meeting. 14/05/14 - the Content Committee has requested that options for a new flag for prescribing status of the VMP to indicate where prescribers should use caution in prescribing by the generic name are explored. 18/08/14 - the Content Committee has considered the options for a new flag. They have concluded that the VMP prescribing status should not be amended because the dm+d data can only be categorical and it is unsuited to indicating where clinical judgement is required. The dm+d cannot be considered a clinical reference source. The Content Committee has agreed that the editorial policy should be updated to clarify the sources for assigning one of the two values for 'VMP not recommended to prescribe' 23/12/14 - the BNF authors intend to make their recommendations for prescribing mesalazine clearer, which will help the dm+d authors in determining whether the prescribing status should change. 12/03/15 - advice is being sought from the MHRA to establish a definitive position for mesalazine products. 13/07/15 - a teleconference is being arranged to establish a definitive position for the VMP prescribing status of products where the MHRA requires a product to have a brand name. 08/10/15 - the MHRA has provided information about how products are licensed and when they require a product to have a brand name. This is complex and cannot easily be reflected in the dm+d data using the current flags for the VMP prescribing status. The utility of the flags will therefore be reviewed. 10/02/16 - the Content Committee has decided that users of dm+d should be consulted about potential changes to the flags for assigning the VMP prescribing status. 03/06/16 - the consultation materials have been drafted and the consultation should be complete by September 2016. 23/06/16 - further changes to the draft consultation materials are in progress and the consultation should begin in September 2016. 27/10/16 - the consultation closes on 14 November 2016 and a decision about the VMP Prescribing Status values will be made after the feedback has been considered. 23/11/16 - the feedback on the survey has been summarised and the analysis will be reviewed by the Content Committee. 20/01/17 - the Content Committee has requested some additional follow up following the initial analysis of the responses to the survey. 28/03/17 - the Content Committee has agreed that changes will be made to the VMP prescribing status values and that the next step is to discuss implementation of the changes with the GPSoC team at NHS Digital. 12/07/17 - Meeting will be arranged with GPSoc. 01/11/17 - MHRA reported that it is their intention to publish an updated MHRA revised policy on the naming of modified release products and outline of when generic substitution can take place (i.e. interchangeability between brand and generics, and between different generics). It was therefore agreed that the dm+d authors would review the VMP prescribing of mesalazine in line with this policy when it is published, and to close the issue. Issue closed.
51 | Tiotropium inhaled products expressing strength as metered dose/delivered dose | NHS RxS | 2017-03-09 | closed | 2017-11-01 | Two VMPs have been authored for tiotropium inhalation powder capsules for two separate AMPs. The two AMPs have different strengths if expressed as the metered dose but have the same delivered dose. A single VMP could therefore cover the two AMPs if the strength is expressed as the delivered dose. How the strength is expressed on the pack differs for the two AMPs. The current VMP names do not specify whether the strength is metered dose or delivered dose. | 09/03/17 - the first AMP to market (Spiriva) has a VMP that expresses the strength as the metered dose (this is in line with the decision of the Content Committee in 2013 that dm+d did not need to change at that time to describe existing products using the delivered dose where the strength is expressed as the metered dose). The second AMP to market (Braltus) has a VMP that expresses the strength as the delivered dose. This is out of line with the Content Committee's decision in 2013 that where a VMP is already authored using the metered dose, there will be no change to the VMP if a new AMP is marketed. The two AMPs should probably both be under the original VMP for Spiriva. However neither the metered dose nor the delivered dose for Braltus would match the expression of strength for the original VMP for Spiriva. Investigations have started into how the VMPs and AMPs should be authored. One option is to author a single VMP that expresses the strength as the delivered dose of tiotropium but this option requires consideration by the Content Committee. If a single VMP is authored it would be given one of the values for the VMP Prescribing Status flag that indicates it is not recommended to prescribe as the VMP. 28/03/17 - options will be identified to ensure the editorial policy supports consistent and appropriate description of the strength of inhaled products as the metered dose / delivered dose. 12/07/17 - consideration is still being given to the proposed options. Concern was raised by the MHRA regarding the option to author both AMPs under one VMP because this creates mismatches between the VMP and AMP strengths, in addition to further disparity in the expression of strength on SmPCs and packaging. The MHRA is carrying out investigation into potential plans to harmonise SmPCs and packaging and will update the Content Committee. 01/11/17 - The introduction of a third inhaler with different delivered and metered doses of tiotropium has further complicated issue. It was decided that the Spiriva and Braltus concepts are to be authored as follows: VMP: Tiotropium 10microgram (delivered dose) inhalation powder capsules with device AMP Spiriva 18microgram (metered dose) inhalation powder capsules with Handihaler AMP: Braltus 10microgram (delivered dose) inhalational powder capsules with Zonda inhaler VMP: Tiotropium 10microgram (delivered dose) inhalation power capsules AMP: Spiriva 18microgram (metered dose) inhalation powder capsules *Since November 2017, authoring of these products in the dm+d has not been updated due to some patient safety concerns being raised e.g. the risk to patients if AMP products aren’t prescribed in view of the different modes of delivery between different types of tiotropium inhalers. Any further update will be communicated via TRUD, and the log will be updated accordingly.*
52 | Describing parenteral dexamethasone as base | NHS Digital | 2018-01-04 | closed | 2018-05-09 | Currently in the paediatric BNF 2017, dosing guidance for parenteral dexamethasone is expressed as the base. However, secondary care prescribing is still based on dexamethasone phosphate. Many guidelines are based on dexamethasone phosphate which the issue raiser says may lead to overdosing if the dose is calculated as the base. The concern is that nursing, medical and pharmacy staff are not clear on whether a dose is based on the salt or base. The enquirer has said it would be very useful if dosing could be clearly stated as dexamethasone base or dexamethasone phosphate. In paediatrics, the difference could be quite significant due to mg/kg dosing. Doses as the base are 150microgramg/kg and dexamethasone phosphate 200 – 250micrograms/kg. | 16/01/2018 - Advised enquirer that the enquiry was being passed onto NHS Digital who would handle the query as it was related to secondary care prescribing for which they have responsibility. 07/03/2018 - It was agreed by the dm+d Content Committee that there would be re-authoring of the 4 parenteral dexamethasone VMPs, and 13 AMPs that are affected. These would be re-authored so that the dexamethasone strength refers to that of the base (and not the salt) and this would bring it in line with the way in which parenteral noradrenaline has been authored. 09/05/2018 - These changes have now been made.
53 | VMP Name strength and Ingredient strength QA | NHSRxS | 2021-07-30 | closed | 2023-02-24 | The VMP Iohexol 755mg/ml (Iodine 350mg/ml) solution for injection 100ml plastic bottles was authored in 2005. This issue revealed that there had been a historical authoring inconsistency between two fields in the dm+d profile of this product. Whilst the VMP description contained the correct base substance strength of iodine (i.e. Iodine 350mg/ml), an incorrect base substance strength had been authored at the VMP ingredient details level (i.e. Iodine 100mg/ml). In 2021, a dm+d native ePMA system in an NHS Trust had used the strength in the VMP Ingredient details field as the master strength data for determining the volume required for dispensing and administering to a patient and this resulted in a near miss (i.e. near patient medication error). | July 2021 30/07/2021 - Issue emailed to nhsbsa.dmdenquiries@nhs.net and email sent back to issue raiser confirming receipt. August 2021 02/08/2021 - Issue raiser contacted and advised this would be corrected for the next national release of dm+d files Discussion takes place between NHSBSA and NHS Digital colleagues and NHSBSA review similar products that include iodine in the VMP name before the next national release of dm+d files. The NHS England Patient Safety Lead is contacted and informed of the issue. NHSBSA identify three further secondary care drug dictionary iodine concepts with errors and correct these too. 04/08/2021 - NHSBSA agree to plan and begin a QA of secondary care dm+d data as well as investigating how to ensure secondary care products are robustly checked as they are progressively authored. 10/08/2021 - NHSBSA pharmacists meet with IT developers to discuss ways of interrogating the dm+d database and to request IT development work this financial year to build in extra validation checks. September, October and November 2021 Secondary care dm+d QA work progresses with respect to comparing and contrasting strength mismatches between VMP names and Ingredient details fields. Circa 4,000 rows of data identifying strength mismatch have been checked to look for anomalies. An exercise follows to further investigate these anomalies. 01/12/2021 - a further 6 historical erroneous strength mismatches identified, corrected and reported via TRUD in the dm+d extract communication available with the weekly dm+d release files. IT developers progress discovery work to investigate building in extra validation checks so that a report can be generated to flag strength mismatches for checking prior to sign off of the dm+d files to be released each week. NHSBSA pharmacists work with data quality experts and explore widening the QA work. 2022 dm+d IT support colleagues have been exploring how to build in extra validation checks June - a report was being tested by IT support to check the coding and the data outputs are correct. July - pharmacists await a copy of this report to review and validate it and see if the report is fit for purpose August, September and October The report generated by IT has been reviewed and implemented into the database. As part of the Quality Assurance process, circa 25,000 ingredient data lines have been checked comparing the VMP Name Strength to the Ingredient Strength. November onwards The IT report will now be run on weekly basis from this point forwards as part of the routine weekly Quality Assurance checks. February 2023 Quality Assurance is ongoing. The primary issue and cross-orgnisational agreement to support investigation and checking of secondary care dm+d has been addressed and therefore this issue is closed.
54 | Naming convention for products expressed with different strengths in the VMP and AMP names | NHSBSA | 2022-07-14 | closed | 2023-05-01 | A concern is expressed that if dm+d uses the VMP strength based on the salt content in the description rather than the strength displayed on the packaging and literature produced by the manufacturer could lead to dispensing/picking errors, e.g. VMP Ibuprofen sodiun dihydrate 200mg tablets and linking AMPs e.g. Nurofen Express 256mg tablets | 04/08/2022 - Following receipt of the issue it was raised at Content Committee meeting. The topic has been discussed by the Committee previously and resulted in the addition of Appendix XX to the dm+d Editorial Policy which listed some examples of VMP and AMP strength mismatches in dm+d and known reasons for these differences supporting dm+d users with increased understanding. A paper summary to be brought to the next Committee meeting following further investigation and consideration of the issue raised 11/08/2022 - Issue raiser updated with next steps 21/11/2022 - Paper brought to the Committee with 3 options: 1 = Do Nothing, 2 = Rename the VMP to Ibuprofen sodium dihydrate 256mg, 3 = Dual name the VMP to Ibuprofen sodium dihydrate 256mg (Ibuprofen 200mg) tablets The Content Committee agreed with option 2 to represent the strengths of Ibuprofen sodium dihydrate and Ibuprofen lysine salts in the VMP descriptions. The Committee was informed that there was an impact on Drug Tariff Part VIIIA naming too. When DHSC and PSNC were able to further clarify the updating of Drug Tarif Part VIIIA, the Drug Tariff and dm+d would be updated in tandem with each other. 10/01/2023 - The issue raiser was provided with the Content Committee update 09/02/2023 - The issue raiser acknowledged welcoming the Content Committee decision March 2023 - updates are to be made to dm+d and the Drug Tariff and to be co-ordinated for April 1st 2023 May 2023 - Updates have been made and the 'Issue' is now closed.
55 | Naming convention for modified release products having different release rates | NHSBSA | 2022-07-14 | closed | 2023-05-01 | Concerns are raised about the dm+d naming conventions where modified release products with different release rates are listed under a single VMP e.g. Diltiazem 120mg modified release capsules. If the product is prescribed generically there is an increased risk of the wrong product being dispensed to a patient as it may not always be apparent to the pharmacist which product with which release profile should be supplied. | 04/08/2022 - Following receipt of the issue it was raised with the Content Committee. The topic has been discussed by the Committee previously and the conclusion then was that dm+d would need to be supported by the likes of approved national pharmacopeial standards for such product descriptions and as these don't exist, the issue was previously closed. DHSC and MHRA colleagues are currently considering similar concerns expressed about modified release morphine and oxycodone products as well as buprenorphine and fentanyl transdermal patches and the outcome of this is likely to influence the next steps here. In the interim NHS Digital and NHSBSA colleagues will explore this latest issue further. 11/08/2022 - Issue raiser updated with next steps 21/11/2022 - The view of the Content Committee was and is that this topic encroaches into the field of clinical decision support which is not supported by the dm+d. Decision support is provided by third party suppliers of prescribing and dispensing systems. dm+d will therefore not be adopting a change in the dm+d naming convention for such products. 10/01/2023 - The issue raiser was provided with the Content Committee update 09/02/2023 - The issue raiser acknowledged being disappointed with the Content Committee decision. The issue raiser is concerned about the large numbers of generic prescriptions being generated and the risks to patient safety if pharmacists are not better supported to ensure the correct products are dispensed. The issue raiser has offered the Content Committee recommendations for how some sample products might be re-authored in dm+d. May 2023 - In the absence of new substantive evidence / information coming to light that merits this topic being re-opened and discussed further, the 'Issue' is now closed.
56 | Drugs with different licensing indications grouped under the same VMP | NHSBSA | 2022-07-14 | closed | 2023-05-01 | Concerns about dm+d listings where two proprietary products with different licensing indications are listed under a single VMP | 04/08/2022 - Following receipt of the issue it was raised with the Content Committee. The Committee was strongly of the opinion that dm+d is not intended as a decision support tool. Consideration of clinical indications is out of the scope of dm+d authoring. 11/08/2022 - Issue raiser contacted and informed that the decision of the dm+d Content Committee was that dm+d is not intended as a decision support tool and that this is out of scope for dm+d but there will be some further discussion. 27/01/2023 - The Issue raiser was provided with a further update that firstly, the dm+d authors do not consider licensed indications in the process of authoring and secondly, the ask therefore to separate products with different licensing indications under different VMPs is considered to fall into the area of clinical decision support and is out of scope. 09/02/2023 - The issue raiser acknowledged being disappointed with the decision. The issue raiser considers that there is some clinical decision support in dm+d and requested more insight into the discussion that has taken place. May 2023 - The dm+d Content Committee has concluded that this falls into the remit of clinical decision support which is outside the scope of the dm+d authoring policy here. The 'Issue' is now closed.
57 | Review of 'Caution-AMP level prescribing advised' marker application | NHSBSA | 2022-07-14 | closed | 2023-05-01 | Concerns that several products are missing the VMP Prescribing Status: 'Caution-AMP level prescribing advised’ as per guidance as per other national expert guidance. Examples include: mycophenolate, tacrolimus and levothyroxine. There are concerns that there is a risk of these products being interchangeably dispensed when prescribed generically without clear dosage instructions if they are recognised as the same formulation. The risk of harm will vary depending on the drug. | 21/11/2022 - Following receipt of the issue it was discussed at Content Committee meeting. The Committee sought follow up support from the MHRA and SPS (Specialist Pharmacy Service) to provide some further insight and view on the issue raised. January 2023 Mycophenolate - SPS reviewed their advice and confirmed they now consider mycophenolate to be suitable for generic prescribing i.e. they have reversed their advice. The Committee therefore decided no changes here in dm+d Levothyroxine - Based on the information available and advice from the MHRA, the Committee decided no change here. The advice is for patients to be kept on a brand by exception only in the event of a specific clinical issue, and this does not include its routine use. Tacrolimus - Based on the information available and advice from the MHRA the Committee decided that oral tacrolimus products should be prescribed by brand. 27/01/2023 - The Issue raiser was provided with the decision of the dm+d Content Committee 09/02/2023 - The issue raiser acknowledged welcoming the Content Committee decision. The issue raiser also asked for dm+d to be cross-referenced with SPS/BNF/MHRA for consideration of any other inconsistencies. February 2023 - All oral tacrolimus VMPs were checked and four were updated in February with the VMP Prescribing Status 'Caution - AMP level prescribing advised’ and this has been communicated via TRUD with the weekly dm+d files release. May 2023 - In the absence of new substantive evidence / information coming to light that merits this topic being re-opened and discussed further, the 'Issue' is now closed.
59 | Ambiuity around Xarelto 1mg/ml Granules for Oral Solution pack sizes and patient safety concerns | NHSBSA | 2023-09-04 | closed | 2024-05-01 | Potential scenarios if prescriber orders 250ml pack size. 1 x 250ml pack (to provide 100ml of the reconstituted volume) may be dispensed & be reimbursed accordingly OR 2 x 250ml & 1 x 100ml packs (to provide 250ml of the reconstituted volume) may be dispensed & reimbursement for only the 250ml pack size. Potential scenarios if prescriber orders 100ml pack size. 1 x 100ml pack (to provide 50ml of the reconstituted volume) may be dispensed & be reimbursed accordingly OR 1 x 250ml pack (to provide 100ml of the reconstituted volume) may be dispensed & reimbursement only for the 100ml pack size ordered. Bottle size as well as the published reconstituted volumes does not reflect the actual usable reconstituted volumes. Pharmacy teams won't always be clear on the prescriber's intentions which could lead to patients being dispensed a different quantity. Increased risk of off-label supply - for e.g., patients may receive 50ml pack size intended for very young children. Owing to the discrepancies around the pack size listings of this product, contractors may encounter reimbursement risks | 09/09/2023 - On the aspect of patient safety, feedback was provided to the issue raiser that Medicines and Healthcare product Regulatory Agency (MHRA) DMRC staff are of the view that the information provided by Bayer PLC Pharmaceuticals is sufficient for safe use. No further action is planned. 09/11/2023 - A paper on Rivaroxaban (Xarelto) dm+d authoring options was taken to the Content Committee. Discussion took place and the committee unanimously agreed that the Xarelto 1mg/ml granules for oral suspension VMPPs/AMPPs are to be described with the volumes of water added for reconstitution. This is the most pragmatic course of action in the absence of final reconstituted volumes being categorically published by the manufacturer. Once it was established which Drug Tarff month updates would be actioned too, the NHSBSA would aim to give the dm+d user community several weeks advance notice with the weekly release of the dm+d files via TRUD. NHSBSA action to summarise the committee's agreed decisions and to draft text to update the Editorial Policy for future reference. 26/02/2024 - Editorial Policy text drafted and brought to the Content Committee for approval. March 2024 - Final Content Committee sign off of Editorial Policy wording. 01/04/2024 - Updates made to dm+d (and the Drug Tariff too). May 2024 - dm+d Editorial Policy published in the public domain with updated text to explain and reflect these changes. The 'issue' is now closed.
60 | Authoring products requiring reconstitution where the quantity displayed on dm+d does not correspond to the actual usable volume after reconstitution as specified in the SmPC. | NHSBSA | 2023-09-14 | closed | 2024-05-01 | Community Pharmacy England (CPE) has identified inconsistencies in the authoring of products that require reconstitution. CPE believes the pack size volumes on dm+d should be based on the usable volume after reconstitution (from product SmPC literature).CPE requested a review of the 'standard' for authoring such products to support the consistency of authoring in dm+d. | 09/11/2023 - Following receipt of the issue, the NHSBSA investigated the dm+d database for relevant and related scenarios. This information was taken to a Content Committee meeting and discussion followed. Following discussion, the committee concluded that basing the dm+d pack size on the usable volume appeared to be the most pragmatic option. However, some scenarios in the future may need to be discussed on a case by case basis. NHSBSA action to summarise the committee's agreed decisions and to draft text to update the Editorial Policy in order to support future referece of this information in the public domain. Once drafted, text to be circulated to the Content Committee for review. 26/02/2024 - Editorial Policy text drafted and brought to the Content Committee for approval. March 2024 - Final Content Committee sign off of Editorial Policy wording. 01/05/2024 - Updates made to dm+d (and the Drug Tariff too). May 2024 - dm+d Editorial Policy published in the public domain with updated text to explain and reflect these changes. The 'issue' is now closed.